## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Product Backlog
| Table 1 | Product Backlog
Sprint Backlog
| Table 1 | Sprint Backlog
Stand up Meeting
| Table 1 | Stand up Meeting
Retrospection
| Table 1 | Retrospection

## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
18-Sep-2025 | 2025-09-18 | M 1 | Objective: Set up foundational database. Tasks include designing schema for flights, setting up DB (SQLite/PostgreSQL), populating with simulated data, and practicing SQL queries (insert, update, joins, transactions, constraints). Output: Functional flight database with sample data. | Must Have | None | Ronak Sharma | Completed
2025-10-02 | 2025-10-02 | M 2 | Objective: Build REST APIs for flight data retrieval and search. Tasks include implementing endpoints, input validation, sorting (price/duration), dynamic pricing based on demand and seat availability, and integrating simulated airline APIs. Output: Working API with pricing logic. | Must Have | Milestone 1 | Ronak Sharma | Completed
2025-10-16 | 2025-10-16 | M 3 | Objective: Implement booking workflow with concurrency safety. Tasks include schema for bookings, seat selection, passenger info, simulated payments, PNR generation, and booking cancellation/history endpoints. Output: End-to-end booking process with concurrency-safe transactions. | Must Have | Milestone 2 | Ronak Sharma | Completed
2025-10-30 | 2025-10-30 | M 4 | Objective: Build frontend interface and integrate APIs. Tasks include designing UI (HTML/CSS/JS/React), connecting flight search & booking APIs, showing dynamic prices, building booking flow UI, and generating booking receipts. Output: Fully functional frontend with backend integration. | Must Have | Milestone 3 | Ronak Sharma | Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[7 empty] | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US001 | T2 | Populate database with simulated flight data | 2025-09-04 | 2025-09-06 | Backend Setup | Done | 10 | bar: Day 1 to Day 3
US001 | T3 | Practice SQL queries (joins, transactions, constraints) | 2025-09-07 | 2025-09-09 | Database Practice | Done | 10 | bar: Day 1 to Day 3
US002 | T4 | Build REST APIs for flight retrieval and search | 2025-09-19 | 2025-09-23 | Backend API Development | Done | 12 | bar: Day 1 to Day 5
US002 | T5 | Implement input validation and sorting | 2025-09-24 | 2025-09-26 | Backend API Enhancement | Done | 8 | bar: Day 1 to Day 3
US002 | T6 | Add dynamic pricing logic and demand simulation | 2025-09-27 | 2025-10-02 | Backend Pricing Logic | Done | 12 | bar: Day 1 to Day 6
US003 | T7 | Design booking schema (flight ID, passenger info, price) | 2025-10-03 | 2025-10-05 | Database Design | Done | 8 | bar: Day 1 to Day 3
US003 | T8 | Develop multi-step booking workflow | 2025-10-06 | 2025-10-10 | Backend Booking Flow | Done | 12 | bar: Day 1 to Day 5
US003 | T9 | Implement concurrency control and cancellation APIs | 2025-10-11 | 2025-10-16 | Transaction Management | Done | 10 | bar: Day 1 to Day 6
US004 | T10 | Design frontend (HTML/CSS/React) | 2025-10-17 | 2025-10-20 | Frontend Design | Done | 10 | bar: Day 1 to Day 4
US004 | T11 | Integrate APIs and display real-time prices | 2025-10-21 | 2025-10-25 | Frontend Integration | Done | 12 | bar: Day 1 to Day 5
US004 | T12 | Generate booking receipts (PDF/JSON) and finalize testing | 2025-10-26 | 2025-10-30 | Frontend Testing | Done | 8 | bar: Day 1 to Day 5
Note on D1: Sumeet Kumar Barua08: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E1: Sumeet Kumar Barua08: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on H2: Sumeet Kumar Barua08: This is the total task estimated in hours for all the user stories
Note on I2: Sumeet Kumar Barua08: Pending effort hours after completion of day 1 work
Note on J2: Sumeet Kumar Barua08: Pending effort hours after completion of day 2 work
Note on K2: Sumeet Kumar Barua08: Pending effort hours after completion of day 3 work
Note on L2: Sumeet Kumar Barua08: Pending effort hours after completion of day 4 work
Note on M2: Sumeet Kumar Barua08: Pending effort hours after completion of day 5 work
Note on N2: Sumeet Kumar Barua08: Pending effort hours after completion of day 6 work
Note on O2: Sumeet Kumar Barua08: Pending effort hours after completion of day 7 work
Note on P2: Sumeet Kumar Barua08: Pending effort hours after completion of day 8 work
Note on Q2: Sumeet Kumar Barua08: Pending effort hours after completion of day 9 work
Note on R2: Sumeet Kumar Barua08: Pending effort hours after completion of day 10 work
Note on S2: Sumeet Kumar Barua08: Pending effort hours after completion of day 11 work
Note on T2: Sumeet Kumar Barua08: Pending effort hours after completion of day 12 work
Note on U2: Sumeet Kumar Barua08: Pending effort hours after completion of day 13 work
Note on V2: Sumeet Kumar Barua08: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Database schema causing duplicate flight entries | Added unique constraint and fixed insert logic
Sprint 1 | Day 4 | API not sorting flights by price correctly | Implemented sort parameter and tested response
Sprint 2 | Day 3 | Dynamic pricing fluctuating too high due to wrong demand factor | Adjusted demand multiplier formula
Sprint 3 | Day 1 | Booking API failing under concurrent requests | Implemented transaction lock and rollback handling
Sprint 3 | Day 3 | PDF receipt generation showing wrong passenger name | Corrected join query in booking summary
Sprint 4 | Day 2 | Frontend prices not updating in real-time | Added useEffect with polling to refresh data

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-09-01 | 2025-09-09 | Backend Team | Maintain consistent naming conventions in DB | Writing SQL without constraints | Practicing SQL joins & normalization | Implemented schema constraints and indexing
2 | 2 | 2025-09-18 | 2025-10-02 | Backend Team | Add input validation and structured logging | Ignoring invalid API requests | Testing APIs with multiple filters | Added error handling and logging middleware
3 | 3 | 2025-10-03 | 2025-10-16 | AI/Backend Team | Improve dynamic pricing logic and simulations | Using static demand multipliers | Analyzing real-time data for price updates | Tuned pricing algorithm with demand factor
4 | 4 | 2025-10-17 | 2025-10-30 | Frontend + Backend Team | Improve UI and API integration | Waiting till last sprint for UI testing | Regular sync between frontend & backend | Completed frontend integration and bug fixes